## Tabelle1
|  | 1 to 100 | 1 to 10
Risk Name | Risk Description | Risk Probability of Occurrence | Risk Impact | Risk response strategy
Not enought time |  | 40% | 10
Underestimated complexity |  | 20% | 5
Unreliability of a team member | A team member doesnt complete his work. | 15% | 7 | The other team member have to plit up the undone work and complete it.