## Tabelle1
|  |  | 1 to 100 | 1 to 10 | 1 to 10
ID | Risk Name | Risk Description | Risk Probability of Occurrence | Risk Impact | Risk factor | Risk migration | Person in charge of tracking
1 | Not enought time | Not finishing our scope of this semester | 60% | 10 | 6 | Careful planning of the sprints. | All
2 | Wrong Priorities | Not focusing on the scope. | 35% | 7 | 2.45 | Not getting carried away by smaller, less needed tasks. | All
3 | Underestimated complexity | The set goals are too hard to achive | 30% | 5 | 1.5 | Self-reflections and changes when sprints are not completed. | Toni Einecker
4 | Coronavirus | Unexpected circumstances (e.g. internet failing, serverhosting platforms not available) | 15% | 8 | 1.2 | Self hosting of a server, other than that there is nothing we could do. | Tobias Bühler
5 | Unreliability of a team member | A team member doesnt complete his work. | 15% | 7 | 1.05 | The other team member have to plit up the undone work and complete it. | Janis Fix
6 | Dataloss | Loss through a github mistake or error. | 5% | 8 | 0.4 | Careful git handling. | Johannes Zipfel
7 | Lose of team members | Losing a team member (e.g. due to failing the exams) | 5% | 5 | 0.25 | Everybody should have knoeledge about the whole code. | All